## Cover
DevMantra Financial Services
SEO Delivery Report — May 2026
Client | Dev Mantra Financial Services
Website | https://www.devmantra.com
Reporting Period | May 2026
Prepared By | Digitech Solutions
Prepared For | Dev Mantra Management Team
Report Date | 13 June 2026
Report Version | v1.0 — Final
Cross-Verified Against | Repo (seo-task-tracker.md) + Notion Client Tasks DB
CROSS-VERIFICATION NOTE
All tasks in this report are verified against two independent sources: (1) the Git repository codebase at C:\xampp\htdocs\Devmantranew\ and (2) the Notion DevMantra Client Tasks database (data_source_id: 7cb0a406-5846-83bb-ad57-87d0b5c3b791). A task is marked DONE only when both sources confirm completion.
AT A GLANCE — MAY 2026
Tasks Completed |  | 10
Tasks Partial |  | 5
Tasks Pending |  | 5
Content Types with SEO Fields |  | 7
DB Migrations Deployed |  | 2
Internal Links Deployed to DB |  | 60+
Codebase Files Created / Modified |  | 20+

## Executive Summary
DevMantra Financial Services — SEO Delivery Report: May 2026
Executive Summary
KEY PERFORMANCE INDICATORS — MAY 2026
| 10 Tasks Completed | 5 Tasks Partial | 5 Tasks Pending | 7 Content Types SEO-Enabled | 60+ Internal Links Deployed
DELIVERY BY PHASE
Phase | Tasks in Phase | Completed | Partial | Pending | Completion %
| Foundation (TASKS 01–08) | 8 | 8 | 0 | 0 | 100%
| Content & Optimisation (TASKS 09–13) | 5 | 1 | 2 | 2 | 20%
| Process & Reporting (TASK 14) | 1 | 0 | 0 | 1 | 0%
| Technical SEO (TASKS 15–20) | 6 | 2 | 2 | 2 | 33%
| TOTAL | 20 | 11 | 4 | 5 | 55%
FULL TASK STATUS REGISTER — MAY 2026
Task ID | Task Title | Phase | Status | Verification Source
TASK 01 | Build Reusable SEO Panel (_seo-panel.blade.php) | Foundation | ✅ DONE | Repo + Notion
TASK 02 | Add Global SEO Settings to Admin Panel | Foundation | ✅ DONE | Repo + Notion
TASK 03 | Build SchemaService.php — Dynamic Schema Engine | Foundation | ✅ DONE | Repo + Notion
TASK 04 | Add SEO Panel to All Admin Edit Views | Foundation | ✅ DONE | Repo + Notion
TASK 05 | Build Dynamic XML Sitemap | Foundation | ✅ DONE | Repo + Notion
TASK 06 | Build Alt Tag Management System | Foundation | ✅ DONE | Repo + Notion
TASK 07 | Fix Broken Meta Tags Across All Content Types | Foundation | ✅ DONE | Repo + Notion
TASK 08 | Gate Tax Calculator with Lead Capture | Foundation | ✅ DONE | Repo + Notion
TASK 09 | Optimise Service Page Meta Tags | Content & Optim. | 🟡 PARTIAL | Repo
TASK 10 | Build Internal Linking Structure (60+ links deployed) | Content & Optim. | ✅ DONE | Repo + Notion
TASK 11 | Write & Publish 10 Priority SEO Blog Posts | Content & Optim. | ❌ PENDING | —
TASK 12 | Bulk Update All Blog Meta Tags (DB) | Content & Optim. | ❌ PENDING | —
TASK 13 | Bulk Add Schema Markup to All Pages | Content & Optim. | 🟡 PARTIAL | Repo
TASK 14 | Monthly SEO Review & Reporting SOP | Process & Reporting | ❌ PENDING | —
TASK 15 | Fix Missing H1 + Homepage Meta Description | Technical SEO | 🟡 PARTIAL | Repo
TASK 16 | Force HTTP → HTTPS Redirect (Site-wide) | Technical SEO | ✅ DONE | Repo + Notion
TASK 17 | NAP Consistency + LocalBusiness Schema | Technical SEO | ✅ DONE | Repo + Notion
TASK 18 | Site Performance Optimisation | Technical SEO | 🟡 PARTIAL | Repo
TASK 19 | PageSpeed Insights Optimisation | Technical SEO | ❌ PENDING | —
TASK 20 | Email Privacy — DMARC/SPF/DKIM | Technical SEO | ❌ PENDING | —

## Completed Tasks
Completed Tasks — May 2026 ¦ Full Detail
Task ID | Task Title | What Was Delivered | File / Evidence | Verification
| TASK 01 | Build Reusable SEO Panel (_seo-panel.blade.php) | • Meta Title field — max 60 chars, live character counter • Meta Description — max 160 chars, live counter • OG Image upload (storage/seo/og-images/) + URL fallback • Canonical URL field • Noindex checkbox — injects 'noindex, nofollow' • Custom Head Code textarea — raw HTML/JSON-LD per page • Collapsible accordion UI — auto-opens on validation errors | resources/views/admin/partials/_seo-panel.blade.php | Repo + Notion ✅
| TASK 02 | Add Global SEO Settings to Admin Panel | • seo_default_title — site-wide fallback title • seo_default_description — fallback meta description • seo_default_og_image — fallback OG social share image • seo_robots_mode — global index/noindex toggle • seo_google_verification — GSC verification tag • seo_ga4_id / seo_gtm_id — tracking IDs • seo_title_separator — configurable (default: —) • Schema config: company name, logo URL, area served | admin/account/settings.blade.php admin/schema/index.blade.php | Repo + Notion ✅
| TASK 03 | Build SchemaService.php (Dynamic Schema Engine) | • organization() — sitewide Organization schema • localBusiness() — LocalBusiness with NAP, hours, sameAs • blogSchema($blog) — BlogPosting for all blogs • caseStudySchema() — Article (case study) • reportSchema() — Report type • newsletterSchema() — Article (newsletter) • serviceSchema($service) — Service type • faqSchema($faqs) — FAQPage with Q&A pairs • breadcrumb($items) — BreadcrumbList on all detail pages • Auto image: og_image → featured_image fallback chain | app/Services/SchemaService.php | Repo + Notion ✅
| TASK 04 | Add SEO Panel to All Admin Edit Views | Wired _seo-panel.blade.php into all 6 content admin views: • admin/blogs/create.blade.php • admin/blogs/edit.blade.php • admin/case-studies/edit.blade.php • admin/newsletters/edit.blade.php • admin/reports/edit.blade.php • admin/services/edit.blade.php | 6 x admin edit/create Blade views | Repo + Notion ✅
| TASK 05 | Build Dynamic XML Sitemap | • Custom SitemapController — queries all published content live • XML template with real lastmod from updated_at timestamps • Route: GET /sitemap.xml added to routes/web.php • .htaccess rewrite — bypasses old static sitemap.xml • Priority: Services 0.90 ¦ Blogs 0.70 ¦ Newsletters 0.60 ⚠ Client Action: Delete old static sitemap.xml on server. Re-submit in Google Search Console. | app/Http/Controllers/SitemapController.php resources/views/sitemap.blade.php | Repo + Notion ✅
| TASK 06 | Build Alt Tag Management System | • image_meta table: rel_path (unique), alt_text, suggestion • POST /admin/media/save-alt — manual alt save • POST /admin/media/suggest-alts — bulk AI generation (Grok) • POST /admin/media/{id}/suggest-alt — single AI suggestion • Artisan command: GenerateImageAltText — bulk generation | app/Models/ImageMeta.php database/migrations/2026_05_07_000002_create_image_meta_table.php | Repo + Notion ✅
| TASK 07 | Fix Broken Meta Tags All Content Types | • Migration 1: SEO columns added to blogs, services, case_studies, reports, newsletters (2026-05-07) • Migration 2: Same fields added to alerts and events (2026-05-12) • All 7 content types now have: meta_title, meta_description, og_image, canonical_url, noindex, custom_head • SEO panel wired to alerts/edit + events/edit admin views • Both controllers validate and save all SEO fields ⚠ Client Action: Run php artisan migrate on production. | database/migrations/2026_05_07_000001_... database/migrations/2026_05_12_000001_... | Repo + Notion ✅
| TASK 08 | Gate Tax Calculator with Lead Capture | • ccGo() in cost-calculator.blade.php checks ccLeadUnlocked flag • If not unlocked → lead capture overlay shown before Step 6 • After lead submit → results auto-load (no friction) • Admin email notification: name, email, phone, company, IP • Email in try/catch — lead always saved even if email fails • Lead stored in calculator_leads table via CalculatorLead model | app/Http/Controllers/CostBenchmarkController.php app/Models/CalculatorLead.php | Repo + Notion ✅
| TASK 10 | Build Internal Linking Structure (60+ links) | 10a: Pillar→Cluster map — 9 service pillars, 8 blogs + 40 newsletters + 1 alert mapped; priority matrix P0–P3 10b: In-content links — 8 anchors via SQL REPLACE() into 7 blogs → Virtual CFO, Corporate Governance, GCC, Risk Advisory, Finance & Compliance, Business Set-up service pages 10c: Related Services callout (gold dm-blog-callout--tip) appended to all 8 blogs — 2 service links each 10d: Related Reading callout (navy dm-blog-callout--info) appended to 7 blogs — cross-blog topical clusters 10e: Alert page (ITCC) — 1 in-content link + callout block; page de-orphaned (was a crawl dead-end) 10f: All 40 newsletters — DEV MANTRA SERVICES block appended; all newsletters de-orphaned in one UPDATE 10g: bulk_internal_links.sql deployed — idempotent, verified | bulk_internal_links.sql step1_internal_link_test.sql Notion: TASK 10a–10g | Repo + Notion ✅
| TASK 16 | Force HTTP → HTTPS Redirect (Site-wide) | • .htaccess: RewriteRule — HTTP→HTTPS + non-www→www (301) • URL::forceScheme('https') in AppServiceProvider (prod only) • Fixed og:url + canonical: url()->current() → request()->url() (strips ?page=, ?tag= query strings from canonical URLs) ⚠ Client Action: Test with curl -I http://devmantra.com → expect 301 to https://www.devmantra.com | public/.htaccess app/Providers/AppServiceProvider.php | Repo + Notion ✅
| TASK 17 | NAP Consistency + LocalBusiness Schema | • localBusiness() in SchemaService sources all NAP data from ContactSetting model — single source of truth • Schema: name, telephone, email, PostalAddress, openingHours, sameAs (social links array) • Rendered on: Homepage, Contact page, all detail pages • Admin-editable at: admin/contact-settings/edit (updating one field updates NAP everywhere automatically) | app/Services/SchemaService.php (localBusiness() method) | Repo + Notion ✅

## Internal Linking Detail
TASK 10 — Internal Linking Deep Dive ¦ 60+ Links Deployed
Source: bulk_internal_links.sql deployed to devmantranew DB ¦ All UPDATEs idempotent (NOT LIKE guards)
SECTION A — In-Content Links via SQL REPLACE() ¦ 8 anchors across 7 blogs
Blog Slug (Shortened) | Anchor Text Phrase | Links To (Service Page) | SQL Method
strengthening-corporate-governance-... | to strengthen governance, the most | /services/corporate-governance | REPLACE()
regulatory-updates-compliance-... | compliance review into the quarterly cadence | /services/finance-accounts-compliance-outsourcing-services | REPLACE()
enabling-scalable-growth-... | combining Virtual CFO, Tax Advisory, and | /services/virtual-cfo-services | REPLACE()
enabling-scalable-growth-... | transfer pricing compliance across new | /services/finance-accounts-compliance-outsourcing-services | REPLACE()
sustainable-growth-budget-2025-... | Innovative financing — green bonds, tax | /services/finance-accounts-compliance-outsourcing-services | REPLACE()
war-is-now-a-tax-on-movement-... | as risk premiums widen | /services/risk-advisory-augmenting-business-process | REPLACE()
wos-vs-llp-vs-branch-office-... | does not just help you enter India | /services/business-set-up-startup-collaboration | REPLACE()
wos-vs-llp-vs-branch-office-... | a regional operating base for global firms | /services/gcc-global-capability-centers | REPLACE()
virtual-vs-fractional-vs-outsourced-cfo-... | Virtual CFO gained traction in India around 2015 | /services/virtual-cfo-services | REPLACE()
SECTION B — Related Services Callout Blocks via SQL CONCAT() ¦ Gold dm-blog-callout--tip
Blog | CSS Class | Service Link 1 | Service Link 2
Corporate Governance blog | dm-blog-callout--tip | /services/corporate-governance | /services/risk-advisory-augmenting-business-process
Regulatory Updates blog | dm-blog-callout--tip | /services/finance-accounts-compliance-outsourcing-services | /services/virtual-cfo-services
Enabling Scalable Growth blog | dm-blog-callout--tip | /services/virtual-cfo-services | /services/finance-accounts-compliance-outsourcing-services
Sustainable Growth blog | dm-blog-callout--tip | /services/finance-accounts-compliance-outsourcing-services | /services/business-set-up-startup-collaboration
War Is Now a Tax... blog | dm-blog-callout--tip | /services/risk-advisory-augmenting-business-process | /services/corporate-governance
WOS vs LLP vs Branch blog | dm-blog-callout--tip | /services/business-set-up-startup-collaboration | /services/gcc-global-capability-centers
Virtual CFO Guide blog | dm-blog-callout--tip | /services/virtual-cfo-services | /services/finance-accounts-compliance-outsourcing-services
India-China Relations blog | dm-blog-callout--tip | /services/gcc-global-capability-centers | /services/business-set-up-startup-collaboration
SECTION C — Related Reading Cross-Links via SQL CONCAT() ¦ Navy dm-blog-callout--info
From Blog | Links To Blog | Topical Relationship | SQL Method
Corporate Governance | War Is Now a Tax on Movement | Governance ↔ Geopolitical Risk | CONCAT()
Enabling Scalable Growth | Virtual vs Fractional vs Outsourced CFO | Strategy ↔ Finance Model | CONCAT()
India–China Relations | WOS vs LLP vs Branch Office | Geopolitics ↔ Market Entry | CONCAT()
Sustainable Growth/Decarbonisation | Regulatory Updates & Compliance | ESG ↔ Compliance | CONCAT()
War Is Now a Tax on Movement | Corporate Governance | Risk ↔ Governance (bidirectional) | CONCAT()
WOS vs LLP vs Branch Office | India–China Relations | Market Entry ↔ Geopolitics (bidir.) | CONCAT()
Virtual vs Fractional CFO | Enabling Scalable Growth | Finance Model ↔ Strategy (bidir.) | CONCAT()
SECTIONS D & E — Alert + Newsletters
Content | Action | Links Deployed | Status
Alert: ITCC Page | In-content REPLACE() + Related Services CONCAT() | 2 service links (Finance & Compliance + Business Set-up) | ✅ De-orphaned
All 40 Newsletters (published) | Bulk CONCAT() — single UPDATE statement | 2 service links each (Finance & Compliance + Virtual CFO) | ✅ All 40 de-orphaned

## Partial Tasks
Partial Tasks — In Progress (Carry Forward to June 2026)
Task ID | Task Title | What Is Done | What Remains | Owner / Next Step
| TASK 09 | Optimise Service Page Meta Tags | • SEO panel wired to services admin • meta_title, meta_description columns exist • Frontend renders fields dynamically | • Audit all service records: SELECT id, name, meta_title, meta_description FROM services • Rewrite any generic/empty meta tags • Ensure titles: Primary Keyword ¦ DevMantra (≤60 chars) • Ensure descriptions: 140–160 chars with CTA | Content / PM Run DB audit first
| TASK 13 | Bulk Add Schema Markup to All Pages | • SchemaService generates all schema types • Homepage: Organization + LocalBusiness + Breadcrumb • All detail pages: type-specific schema + Breadcrumb • Alert + Event schema added in May sprint • custom_head field on all 7 content types | • Verify FAQ schema renders on service/blog pages with FAQ sections • Bulk-populate custom_head for existing content via admin • Run Google Rich Results Test on blog + service URLs | Dev / QA Google Rich Results Test first
| TASK 15 | Fix Missing H1 + Homepage Meta | • Global seo_default_title + seo_default_description in settings • Frontend layout renders meta dynamically | • Confirm homepage has exactly 1 <h1> tag in rendered HTML • Audit homepage meta description — should be >120 chars, keyword-rich, CTA • Check resources/views/frontend/home.blade.php NOTE: H1 fix shipped in June sprint — verify on prod | Dev: View source / Inspect PM: Update homepage meta in admin settings
| TASK 18 | Site Performance Optimisation | • loading=lazy on all below-fold images (6 detail views) • Browser caching in .htaccess (images: 1yr, CSS/JS: 1mo) • Gzip compression configured in .htaccess | • Run npm run build → upload minified assets to production • Enable HTTP/2 in cPanel → MultiPHP Manager • Run PageSpeed Insights (mobile + desktop) — record baseline • Convert uploaded JPGs/PNGs to WebP format | Dev: npm run build + deploy Client: Enable HTTP/2 in cPanel PM: Record PageSpeed score baseline
| TASK 13 — Additional | Schema: Alerts + Events Admin Panel | • alert-detail.blade.php: NewsArticle schema + Breadcrumb auto-generated • events.blade.php: Event schema + Breadcrumb auto-generated • custom_head field available for manual JSON-LD injection | • Fill meta_title + meta_description for all existing alert/event records via admin • Run php artisan migrate on production first | PM: Admin content entry task (Migrate first)

## Pending Tasks
Pending Tasks — Queued for Upcoming Sprints
Task ID | Task Title | Reason Deferred | Work Required | Dependency
| TASK 11 | Write & Publish 10 Priority SEO Blogs | Content task — requires keyword research + brief sign-off before writing | • Identify 10 target keywords (volume + low competition) • Draft 10 blog posts: min 1,500 words each • Each post: meta_title, meta_description, og_image, in-content service links, schema • Publish via admin panel | Keyword research (precedes writing)
| TASK 12 | Bulk Update All Blog Meta Tags (DB) | Depends on content audit; follows TASK 11 keyword mapping | • Run audit: find all blogs, reports, newsletters, case studies with NULL or generic meta fields • Generate optimised meta_title + meta_description for each • Bulk update via DB seed or artisan command | Keyword map (TASK 11) DB audit query first
| TASK 14 | Monthly SEO Review & Reporting SOP | Process/document task — deferred until technical foundation stable | • Define monthly SEO review checklist (rankings, traffic, crawl errors, Core Web Vitals) • Set up GSC + GA4 reporting cadence • Create reporting template (Notion / Sheets) • Document SOP: who reviews, what tools, what actions | None — can start now Recommend June sprint
| TASK 19 | PageSpeed Insights Optimisation | Requires live site baseline (TASK 18) before targeted fixes | • Run pagespeed.web.dev on homepage — get LCP, CLS, FID • Target: Mobile ≥ 80, Desktop ≥ 90 • Add fetchpriority=high to hero LCP image • Address Lighthouse-specific issues • Google Fonts already non-blocking (media=print trick done) | TASK 18 baseline first (live site required)
| TASK 20 | Email Privacy — DMARC/SPF/DKIM | DNS-level task — requires cPanel access by client; cannot be code-deployed | • Verify SPF record: v=spf1 include:... ~all • Add DKIM (generate via cPanel Email → Email Deliverability) • Add DMARC: v=DMARC1; p=quarantine; rua=mailto:dgtechsolutions23@gmail.com • Test: https://mxtoolbox.com/dmarc.aspx • Verify email headers for DMARC pass | Client: cPanel access DNS zone editor

## Client Action Items
Client & PM Action Items — Required to Complete Deployment
These items cannot be deployed by code — human action required on the production server or admin panel
SERVER / DEPLOYMENT ACTIONS (Dev / Hosting)
# | Action | Detail / Steps | Related Task | Priority
| 1 | Run php artisan migrate on production | Applies 3 new DB migrations: • 2026_05_07_000001 — SEO fields on 5 content tables • 2026_05_07_000002 — image_meta table • 2026_05_12_000001 — SEO fields on alerts + events | TASK 07 | 🔴 HIGH
| 2 | Delete old static sitemap.xml from server | File location on host: /home2/devmasjc/public_html/sitemap.xml Delete it — the new dynamic controller (SitemapController.php) replaces it via .htaccess rewrite | TASK 05 | 🔴 HIGH
| 3 | Re-submit sitemap in Google Search Console | GSC → Sitemaps → Remove old → Add: https://www.devmantra.com/sitemap.xml Verify it shows green status | TASK 05 | 🔴 HIGH
| 4 | Deploy blade/PHP code changes to production | Upload all changed files from local XAMPP to cPanel. Then run: php artisan view:cache | ALL | 🔴 HIGH
| 5 | Test HTTPS redirect after deploy | Run: curl -I http://devmantra.com → Expect: 301 to https://www.devmantra.com Also test: curl -I https://devmantra.com (non-www) → Expect: 301 to https://www.devmantra.com | TASK 16 | 🟡 MEDIUM
| 6 | Run Google Rich Results Test | Test a blog URL and a service URL at: https://search.google.com/test/rich-results Verify: BlogPosting, Service, BreadcrumbList schema detected | TASK 03, 13 | 🟡 MEDIUM
| 7 | Enable HTTP/2 in cPanel | cPanel → MultiPHP Manager → Enable HTTP/2 Or contact hosting provider | TASK 18 | 🟡 MEDIUM
| 8 | Run npm run build — upload minified assets | On local machine: npm run build Upload: /public/build/ folder to production server | TASK 18 | 🟡 MEDIUM
| 9 | Run PageSpeed Insights — record baseline | https://pagespeed.web.dev → enter devmantra.com homepage Record: Mobile score, Desktop score Target: Mobile ≥ 80, Desktop ≥ 90 | TASK 18, 19 | 🟡 MEDIUM
CONTENT / ADMIN ACTIONS (PM / Content Team)
# | Action | Detail / Steps | Related Task | Priority
| 1 | Fill meta tags for alerts + events in admin | Go to Admin → Alerts → Edit each alert → fill meta_title + meta_description Repeat for Events Do this AFTER running migrate | TASK 07, 12 | 🟡 MEDIUM
| 2 | Audit + rewrite service page meta tags | Run: SELECT id, name, meta_title, meta_description FROM services Rewrite any generic or empty meta_title (max 60 chars: Primary Keyword ¦ DevMantra) Rewrite descriptions: 140–160 chars with CTA | TASK 09 | 🟡 MEDIUM
| 3 | Set up DMARC/SPF/DKIM DNS records | Log into cPanel DNS Zone Editor: • Verify SPF: v=spf1 include:... ~all • Add DKIM (cPanel → Email → Email Deliverability) • Add DMARC TXT record Test at: https://mxtoolbox.com/dmarc.aspx | TASK 20 | 🟡 MEDIUM
| 4 | Run bulk meta fix SQL in phpMyAdmin | File: SEO/sql/01_onpage_meta_fixes_2026-06-13.sql Run in phpMyAdmin → devmantranew database → SQL tab Backs up first! This strips duplicate brand suffix from meta_titles + backfills canonical_url | TASK 07 | 🟡 MEDIUM

## Validation & Appendix
Validation Index & Appendix — How to Independently Verify Every Task
This sheet is for the review team. Every completed task can be independently verified using the steps below.
SECTION 1 — VERIFICATION INDEX: HOW TO CHECK EACH COMPLETED TASK
Task | How to Verify | Expected Result | Tool / Access
| TASK 01–04 (SEO Panel + Admin) | Search codebase for @include in admin views: grep -r '_seo-panel' resources/views/admin/ | Should appear in: blogs/create, blogs/edit, case-studies/edit, newsletters/edit, reports/edit, services/edit | Terminal / VS Code search
| TASK 05 (Dynamic Sitemap) | Visit: http://127.0.0.1:8000/sitemap.xml (or https://www.devmantra.com/sitemap.xml on prod) | Returns live XML with <url> entries for all published blogs, services, reports, newsletters, etc. | Browser / cURL
| TASK 06 (Alt Tag System) | In phpMyAdmin: SELECT * FROM image_meta LIMIT 10 | Table exists with rel_path and alt_text columns | phpMyAdmin → devmantranew
| TASK 07 (Meta Tags — 7 Types) | In phpMyAdmin: SHOW COLUMNS FROM blogs; SHOW COLUMNS FROM alerts; | Both tables show: meta_title, meta_description, og_image, canonical_url, noindex, custom_head columns | phpMyAdmin → devmantranew
| TASK 08 (Lead Gate Calculator) | Open: http://127.0.0.1:8000/calculator Click through to Step 6 (Results) without submitting a lead | Lead capture overlay appears and blocks access to results | Browser — local XAMPP
| TASK 10 (Internal Linking — Blogs) | In phpMyAdmin: SELECT slug, IF(content LIKE '%dm-blog-callout%','HAS CALLOUT','MISSING') AS callout FROM blogs | All 8 blog slugs show: HAS CALLOUT | phpMyAdmin → devmantranew → blogs table
| TASK 10 (Internal Linking — In-Content) | In phpMyAdmin: SELECT slug, IF(content LIKE '%/services/virtual-cfo-services%','✓','✗') AS vcfo_link FROM blogs | Rows for virtual-vs-fractional-... and enabling-scalable-growth-... show ✓ | phpMyAdmin → devmantranew → blogs table
| TASK 10 (Internal Linking — Newsletters) | In phpMyAdmin: SELECT COUNT(*) FROM newsletters WHERE status='published' AND content LIKE '%DEV MANTRA SERVICES%' | Returns 40 (all published newsletters have the service block) | phpMyAdmin → devmantranew → newsletters table
| TASK 10 (Internal Linking — Alert) | In phpMyAdmin: SELECT slug, IF(content LIKE '%finance-accounts-compliance%','✓','✗') AS link FROM alerts | Row for importance-process-of-income-tax-clearance-certificate shows ✓ | phpMyAdmin → devmantranew → alerts table
| TASK 16 (HTTPS Redirect) | On production: curl -I http://devmantra.com | Returns: HTTP/1.1 301 Moved Permanently Location: https://www.devmantra.com/ | Terminal / cURL (production only)
| TASK 17 (LocalBusiness Schema) | View source on homepage → Ctrl+F → search: LocalBusiness | JSON-LD block with @type: LocalBusiness visible in page source | Browser → View Source (Ctrl+U)
| TASK 03 (BlogPosting Schema) | View source on any blog page → Ctrl+F → search: BlogPosting | JSON-LD block with @type: BlogPosting visible, contains headline, datePublished, author | Browser → View Source (Ctrl+U)
| TASK 03 (Google Rich Results) | Paste a blog or service URL into: https://search.google.com/test/rich-results | Detected items: BlogPosting / Service + BreadcrumbList — all green | Google Rich Results Test (no login)
SECTION 2 — NOTION DATABASE REFERENCE
| Database | DevMantra Client Tasks
| Data Source ID | 7cb0a406-5846-83bb-ad57-87d0b5c3b791
| Parent | Dev Mantra Client Portal
| Filter Applied for This Report | Status = Completed AND Completed On between 2026-05-01 and 2026-05-31
| Task 10 Sub-tasks in Notion | TASK 10a through TASK 10g — all marked Completed, dated May 2026
| Notion URL (Tasks DB) | https://app.notion.com/p/5560a406584682fb85cc01fde163c142
SECTION 3 — REPOSITORY FILE REFERENCE
Purpose | File Path | Task Covered | Notes
SEO Partial (Admin Panel) | resources/views/admin/partials/_seo-panel.blade.php | TASK 01 | Reusable component
Schema Engine | app/Services/SchemaService.php | TASK 03, 17 | All schema types here
Dynamic Sitemap Controller | app/Http/Controllers/SitemapController.php | TASK 05 | Queries DB live
Sitemap XML Template | resources/views/sitemap.blade.php | TASK 05
Alt Tag Model | app/Models/ImageMeta.php | TASK 06
Lead Capture Model | app/Models/CalculatorLead.php | TASK 08
Calculator Controller | app/Http/Controllers/CostBenchmarkController.php | TASK 08 | Lead gate logic here
Frontend Layout (meta out) | resources/views/layouts/frontend.blade.php | TASK 01–07 | Renders all meta tags
SEO Migration — 5 tables | database/migrations/2026_05_07_000001_add_seo_fields_to_content_tables.php | TASK 07 | blogs, services, case_studies, reports, newsletters
Alt Tag Migration | database/migrations/2026_05_07_000002_create_image_meta_table.php | TASK 06
Alerts + Events SEO Migr. | database/migrations/2026_05_12_000001_add_full_seo_fields_to_alerts_and_events.php | TASK 07
Internal Linking Bulk SQL | bulk_internal_links.sql | TASK 10 | 5 sections, idempotent
Int. Linking Step-1 SQL | step1_internal_link_test.sql | TASK 10 | Single-blog test first
SEO Task Tracker | SEO/seo-task-tracker.md | ALL | Master source of truth
SEO Delivery Report (MD) | SEO/devmantra-seo-may-2026-delivery-report.md | ALL | This report source
SECTION 4 — GLOSSARY OF TERMS
| JSON-LD | JavaScript Object Notation for Linked Data — Google's preferred format for structured data / schema markup
| NAP | Name, Address, Phone — the three core local SEO fields that must be consistent across all pages and directories
| OG Image | Open Graph image — the thumbnail shown when a page is shared on LinkedIn, Facebook, Twitter
| Canonical URL | The definitive URL for a page — tells Google which version to index when multiple URLs show the same content
| Noindex | Meta tag that instructs search engines not to index a page
| Idempotent SQL | SQL that is safe to run multiple times — produces the same result regardless of how many times it runs
| SQL REPLACE() | MySQL function that replaces an exact text string within a column value — used for in-content link injection
| SQL CONCAT() | MySQL function that appends text to the end of a column value — used for callout block appending
| BlogPosting | Google structured data type for blog articles — enables rich results in SERPs
| BreadcrumbList | Structured data type that renders breadcrumb navigation in Google search results
| FAQPage | Structured data type that renders FAQ dropdowns in Google search results (AEO signal)
| Pillar Page | A comprehensive service/topic page that acts as the hub for a cluster of related blog content
| Cluster Page | A blog or supporting content page that links back to its pillar page
| De-orphaned | A page that previously had no internal links pointing to it — now has inbound links and is reachable in site crawl
| dm-blog-callout--tip | Existing CSS class on devmantra.com — renders a gold styled callout box (Related Services)
| dm-blog-callout--info | Existing CSS class on devmantra.com — renders a navy styled callout box (Related Reading)
Report compiled: 13 June 2026 ¦ Prepared by: Digitech Solutions ¦ For: Dev Mantra Financial Services Management Team ¦ Version: v1.0 Final